## TaskList
Feature | Task | Priority | Difficulty | Time Estimate | Description
General
Testing | In-Game testing | 2 | 1 | 15 | Test the game
R&D | Learn about Unity | 1 | 1 | 15
| Learn about JsonFx | 3 | 1 | 2
Graphics
Map | Create Map | 1 | 1 | 1 | For Level Select Scene
Particle Effects | Create different effects | 3 | 2 | 5 | Magic effects (fire, lightning, ice, etc)
Enemies | Create Enemy Sprites | 1 | 1 | 5 | Sprites for enemies
Items | Create melee weapons | 2 | 1 | 5 | Create the melee weapons to be used in the game
| Create bows | 2 | 1 | 5 | Create the bows to be used in the game
| Create shields | 2 | 1 | 5 | Create the shields to be used in the game
| Create misc items | 2 | 1 | 5 | Create the misc items to be used in the game
UI | Create Icons for melee,arrow,magic,block,coin, repair, and potion | 2 | 1 | 2 | For the icon spawner
| Create HUD, button, and any background graphics | 2 | 1 | 2 | Graphics for buttons, the HUD, and any menu or combat backgrounds
Mechanics
General | Store System | 1 | 3 | 5 | System for buying and selling items at the store
| Icon Spawner | 1 | 4 | 10 | System for spawning in the correct icons
| Enemy Spawner | 1 | 4 | 10 | System for spawning in enemies
Player | Inventory System | 1 | 3 | 8 | System for managing all the items the player has
| PlayerStats System | 2 | 1 | 4 | System for leveling up your stats
| Saving Player information | 2 | 2 | 5 | Save Player progress, such as inventory and player stats
Enemy | Enemy States | 1 | 2 | 2 | MOVING, ATTACKING, DEAD
| Enemy Movement | 1 | 2 | 5 | How the enemy moves
| Enemy Attack | 1 | 3 | 5 | How the enemy attacks
| Enemy Death | 2 | 1 | 2 | Enemy Dies
| Base Enemy | 1 | 2 | 7 | A base enemy class with generic movement and attack
| Base Boss | 2 | 2 | 7 | A Base Boss class
Icon | Create CoinIcon class
Create MagicIcon class
Create RangedIcon class
InventoryItem
Controls | Create HealthControl
Create ManaControl
Create WeaponControl
Create ShieldControl
UI
Menu | Create the start scene | 3 | 1 | 1 | Scene the game starts with, tap start game
| Create the level select screen | 1 | 2 | 3 | Scene for selecting the next level or access other scenes
| Create the inventory scene | 1 | 1 | 6 | Scene for equipping weapons, shields, and magic
| Create the store scene | 1 | 3 | 6 | Scene for purchasing and selling weapons, shields, potions, and repair hammers
| Create the character scene | 2 | 2 | 4 | Scene for looking at your stats and leveling them up
| Create the level scene | 1 | 3 |  | Scene for representing a level in game
In Game | Create Coin Bag | 2 | 2 | 3 | Collects coin icons as they are thrown
HUD | Display Player's health and other information | 1 | 2 | 4 | Will display your health and any other important information
| Display Enemy's health | 1 | 2 | 1 | Will display enemies health
Sound
Audio | Find music and sound effects | 3 | 1 | 5 | Find sound effects for weapon attacks, magic attacks, arrows, enemy attacks, blocking attacks, collecting coins, drinking potion, using repair hammer. Music for menu and combat, selecting menu items. Any weather sounds.
| Implement menu music | 4 | 1 | 1 | when in any menu play menu music
| Implement background music | 4 | 1 | 1 | When in combat music will play in the background
| Implement weapon sounds | 3 | 3 | 4 | When you attack with a weapon, the appropriate sound should be played
| Implement shield sounds | 3 | 3 | 4 | When you defend with a shield, the appropriate sound should be played
| Implement magic sounds | 3 | 3 | 4 | When you attack with magic, the appropriate sound should be played
| Implement misc sounds | 4 | 2 | 2 | When drinking a potion, using a repair hammer, or selecting something in a menu, the appropriate sound should be played
|  |  | Total: | 186

## Tasks 02-11 to 02-18
Task | Time Estimated to Complete | Time Spent | Over/Under | Assigned To | Status | Notes
Expand MagicIcon class | 3 |  |  | James | TODO
Have IconSpawner Spawn in new icons when old ones are used | 1.5 | 0.5 | -1 | James | Done
Fix Base Enemy Collisions with weapon | 1 | 0.5 | -0.5 | James | Done | And make variables public
Create StandingEnemy Class | 2 |  |  | James | TODO | Will be like a wolf
Create FlyingEnemy Class | 4 |  |  | James | TODO
Create Base Boss Class | 3 |  |  | James | TODO
Create ComparedItem Game Object | 2 |  |  | James | TODO | Still need to alter to show compared magic when looking at magic section
Fix Icons and enemies colliding with each other | 3 | 1 | -2 | James | Done
Research and implement Finite state machine for enemy | 4 | 4 |  | James | In Progress
Reduce coupling/Clean up code | 2 | 2.25 | 0.25 | James | Done
Change name of enemy methods to OnXXX | 0.25 | 0.25 |  | James | Done
Update MeleeWeapon to take in a prefab and itemImage | 0.5 | 0.5 |  | James | Done
Total Hours Assigned | 26.25 | 9
TODO
In Progress
Done

## Tasks 02-04 to 02-11
Task | Time Estimated to Complete | Time Spent | Over/Under | Assigned To | Status | Notes
Add a RigidBody to the base icon | 0.5 | 0.5 | 0 | James | Done
Create MagicIcon | 1 | 1 | 0 | James | Done
Create CoinIcon | 1 | 0.5 | -0.5 | James | Done | Adds a coin when colliding with coinbag
Create RangedIcon | 1 | 1.5 | 0.5 | James | Done
Have IconSpawner Spawn in new icons when old ones are used | 2.5 | 0.5 |  | James | In Progress
Create Base Enemy Class | 5 | 6 | 1 | James | In Progress | Issue occurring with collisions
Create EnemyPrefab | 0.5 | 0.5 | 0 | James | Done |  | TODO
Create EnemySpawner | 1 | 1 | 0 | James | Done | Will Spawn in Enemy Prefab | In Progress
Create ComparedItem Game Object | 2 |  |  | James | TODO | Still need to alter to show compared magic when looking at magic section | Done
Add iconselect boolean to prevent multiple icons being selected | 0.25 | 0.25 | 0 | James | Done
Script Cleanup | 1 | 1.5 | 0 |  | Done
Total Hours Assigned | 14 | 12.75

## Tasks 01-28 to 02-04
Task | Time Estimated to Complete | Time Spent | Over/Under | Assigned To | Status | Notes
Fill inventory Class with Fake data | 1 | 0.5 | -0.5 | James | Done
Create ActionArea | 1 | 0.5 | -0.5 | James | Done | Appears when the WeaponControl is in use
Create WeaponControl and attach to WeaponControl Game Object | 2 | 2 | 0 | James | Done
Create ShieldControl and attach to ShieldControl Game Object | 2 | 1 | -1 | James | Done | Will not do to much until the enemy is created
Filter InventoryItems based on itemType for Inventory Scene | 2 | 2 | 0 | James | Done
Select inventoryItem with touch in Inventory Scene | 1.5 | 1 | -0.5 | James | Done
Create ComparedItem Game Object | 2 | 2 | 0 | James | In Progress | Still need to alter to show compared magic when looking at magic section
Create SelectedItem Game Object | 2 | 1.25 | -0.75 | James | Done | Game Object will display the select item's information | TODO
Reduce rows in Inventory scene and make slots bigger | 0.5 | 0.25 | -0.25 | James | Done |  | In Progress
Rearrange Inventory Scene UI | 0.5 | 0.25 | -0.25 | James | Done | To show number of health potions and mana potions the player has | Done
Create Sky,Ground, and Background Game Objects | 0.5 | 0.25 | -0.25 | James | Done
Convert unequippedItems to a List | 1 | 0.25 | -0.75 | James | Done
Create Icon Base Class | 2 | 2 | 0 | James | Done | Icon Spawner can spawn these in
Total Hours Assigned | 18 | 13.25