## TaskList
Feature | Task | Priority | Difficulty | Time Estimate | Description
General
Testing | In-Game testing | 2 | 1 | 15 | Test the game
R&D | Learn about Unity | 1 | 1 | 15
| Learn about JsonFx | 3 | 1 | 2
Graphics
Map | Create Map | 1 | 1 | 1 | For Level Select Scene
Particle Effects | Create different effects | 3 | 2 | 5 | Magic effects (fire, lightning, ice, etc)
Enemies | Create Enemy Sprites | 1 | 1 | 5 | Sprites for enemies
Items | Create melee weapons | 2 | 1 | 5 | Create the melee weapons to be used in the game
| Create bows | 2 | 1 | 5 | Create the bows to be used in the game
| Create shields | 2 | 1 | 5 | Create the shields to be used in the game
| Create misc items | 2 | 1 | 5 | Create the misc items to be used in the game
UI | Create Icons for melee,arrow,magic,block,coin, repair, and potion | 2 | 1 | 2 | For the icon spawner
| Create HUD, button, and any background graphics | 2 | 1 | 2 | Graphics for buttons, the HUD, and any menu or combat backgrounds
Mechanics
General | Store System | 1 | 3 | 5 | System for buying and selling items at the store
| Icon Spawner | 1 | 4 | 10 | System for spawning in the correct icons
| Enemy Spawner | 1 | 4 | 10 | System for spawning in enemies
Player | Inventory System | 1 | 3 | 8 | System for managing all the items the player has
| PlayerStats System | 2 | 1 | 4 | System for leveling up your stats
| Saving Player information | 2 | 2 | 5 | Save Player progress, such as inventory and player stats
Enemy | Enemy States | 1 | 2 | 2 | MOVING, ATTACKING, DEAD
| Enemy Movement | 1 | 2 | 5 | How the enemy moves
| Enemy Attack | 1 | 3 | 5 | How the enemy attacks
| Enemy Death | 2 | 1 | 2 | Enemy Dies
| Base Enemy | 1 | 2 | 7 | A base enemy class with generic movement and attack
| Base Boss | 2 | 2 | 7 | A Base Boss class
Icon | Create CoinIcon class
Create MagicIcon class
Create RangedIcon class
InventoryItem
Controls | Create HealthControl
Create ManaControl
Create WeaponControl
Create ShieldControl
UI
Menu | Create the start scene | 3 | 1 | 1 | Scene the game starts with, tap start game
| Create the level select screen | 1 | 2 | 3 | Scene for selecting the next level or access other scenes
| Create the inventory scene | 1 | 1 | 6 | Scene for equipping weapons, shields, and magic
| Create the store scene | 1 | 3 | 6 | Scene for purchasing and selling weapons, shields, potions, and repair hammers
| Create the character scene | 2 | 2 | 4 | Scene for looking at your stats and leveling them up
| Create the level scene | 1 | 3 |  | Scene for representing a level in game
In Game | Create Coin Bag | 2 | 2 | 3 | Collects coin icons as they are thrown
HUD | Display Player's health and other information | 1 | 2 | 4 | Will display your health and any other important information
| Display Enemy's health | 1 | 2 | 1 | Will display enemies health
Sound
Audio | Find music and sound effects | 3 | 1 | 5 | Find sound effects for weapon attacks, magic attacks, arrows, enemy attacks, blocking attacks, collecting coins, drinking potion, using repair hammer. Music for menu and combat, selecting menu items. Any weather sounds.
| Implement menu music | 4 | 1 | 1 | when in any menu play menu music
| Implement background music | 4 | 1 | 1 | When in combat music will play in the background
| Implement weapon sounds | 3 | 3 | 4 | When you attack with a weapon, the appropriate sound should be played
| Implement shield sounds | 3 | 3 | 4 | When you defend with a shield, the appropriate sound should be played
| Implement magic sounds | 3 | 3 | 4 | When you attack with magic, the appropriate sound should be played
| Implement misc sounds | 4 | 2 | 2 | When drinking a potion, using a repair hammer, or selecting something in a menu, the appropriate sound should be played
|  |  | Total: | 186

## TODO
What is left to do? | Notes | Completion | Time Estimate (in hours) | Status
Audio for the entire game | Enemy sounds, Weapon sounds | 75% | 4
Create more Weapons and shields |  | 0% | 12
Particle effects for all magic and enemies |  | 80% | 8
Inventory Scene | May need a bit of polish | 90% | 5
Store Scene | May need a bit of polish | 90% | 5
Load and Save Player stats and inventory | Save Player stats and Inventory | ~100% | ~0 | Done
Player leveling up(player being able to control their stats) | Allow player to increase their stats | ~100% | ~0 | Done
Player stats being taken into effect | Mana and Stamina costs reflected by Player stats | ~100% | 0 | Done
Enemy animations | Move, attack, die | 0% | 25
Boss Enemies and their special attacks | Yeti, Giant, and Dragon | 25% | 10
Combat System | Polish/fix an potential bugs | 80% | 6

## BackLog
Task | Time Estimated to Complete | Time Spent | Over/Under | Assigned To | Status | Notes
Create ImprisonmentMagic | 1 |  |  | James | TODO
Create PoisonMagic | 1 |  |  | James | TODO
Create BarrierMagic | 3 |  |  | James | TODO
Create HealthMagic | 1 |  |  | James | TODO
Weapon always appears under actionarea | 2 |  |  | James | TODO
Enemy death is delayed if continually attacking enemy | 2 |  |  | James | TODO
Sound Effects for the Player | 4 |  |  | James | TODO
Adjust enemy speeds to increase difficulty | 2 |  |  | James | TODO

## Tasks 04-01 to 04-08
Task | Time Estimated to Complete | Time Spent | Over/Under | Assigned To | Status
Icons cut to the right when thrown | 1 |  |  | James | TODO
Fix stopping StandingEnemy | 2 |  |  | James | TODO
Push Perspective back | 3 |  |  | James | TODO
Deal with multiple enemies | 1 |  |  | James | TODO
Display hit points when attacking | 1 |  |  | James | TODO
Add more bosses | 10 |  |  | James | TODO
Fix enemy shrinking when slowed down | 3 |  |  | James | TODO
Hours Assigned | 21 | 0
Total Hours | 21
Done
TODO
InProgress

## Tasks 03-25 to 04-01
Task | Time Estimated to Complete | Time Spent | Over/Under | Assigned To | Status | Notes
Add UI Sound Effects | 2 | 3 |  | James | Done | Add magic equip sound effect, rangedIconSound effect, frost blast sound effect, fireblast sound effect, potion drank sound effect
Icons cut to the right when thrown | 1 |  |  | James | TODO | Fix issue
PlayerStats being taken into effect | 1 | 0.5 |  | James | Done | Replace Luck with Wisdom
Add Sound Effects for Enemies | 5 | 8.5 |  | James | Done | Sound for attack, die, hit and stand/move
Fix stopping StandingEnemy | 2 |  |  | James | TODO | StandingEnemy moves slightly when they should always be standing
Add Enemy Burning effect | 3 | 2 |  | James | Done | with sound
Add Enemy Froze Effect | 4 | 2.5 |  | James | Done | with sound
Add Particle effect to Lightning Magic | 3 | 2 |  | James | Done | with sound
Improved Fire and Frost particle effects | 1 | 1 |  | James | Done | Added better particle effects
Add Enemy Electrocuted Sound Effect | 1 | 1 |  | James | Done
Hours Assigned | 21 | 20.5
Total Hours | 23
Done
InProgress

## Tasks 03-18 to 03-25
Task | Time Estimated to Complete | Time Spent | Over/Under | Assigned To | Status | Notes
Add UI Sound Effects | 2 | 3 |  | James | InProgress | Add sound effects to store and Inventory
Prevent shield use after Defence is 0 | 2 | 1 | -1 | James | Done | Prevent player from selecting shield
Create Temporary Coin holding | 1 | 0.5 | -0.5 | James | Done | In order to not collect coins if the Player losses the level
Setup InventorySlots in Store Scene to load either Player or clerks inventory | 5 | 5 |  | James | Done
Be able to buy or sell selected item in Store Scene | 3 | 2.5 | -0.5 | James | Done
Implement Character Level up Screen | 8 | 4 | -4 | James | Done
Fix Taps stopping when a coin is collected | 1 | 0.5 | -0.5 | James | Done | When the player holds onto a coin icon and drags it to the coinbag without letting go
Icons cut to the right when thrown | 1 |  |  | James | TODO
Fix Button not switching between Buy and Sell mode | 1 | 0.5 | -0.5 | James | Done | Need to dynamically set the button listener
Sold Items are added to the clerks inventory | 1.5 | 1 | -0.5 | James | Done
Save LeveledUp stat in PlayerStats to store if the player has leveled up | 1 | 0.5 | -0.5 | James | Done | In case player exits game before leveling up their character
PlayerStats being taken into effect | 4 | 2 | -2 | James | InProgress
Hours Assigned | 21 | 20.5
Total Hours | 30.5

## Tasks 03-11 to 03-18
Task | Time Estimated to Complete | Time Spent | Over/Under | Assigned To | Status | Notes
Create Projectile class | 1.5 | 1 | -0.5 | James | Done
Improve Collision(change to OnTriggerStay2D) | 1.5 | 0.5 | -1 | James | Done
Have Shield work with enemy projectiles | 1.5 | 1 | -0.5 | James | Done | Created Derived projectile classes
Fix Boss Special Attack spawning issue | 1 | 0.5 | -0.5 | James | Done | Special attack was constantly spawning
Fix Particle Stopping | 2 | 1.5 | -0.5 | James | Done | Particles were rendering behind sprite
Implement Saving and Loading of Player class | 3 | 2 | -1 | James | Done
Have Icons move with IconSlots and be able to pause icon movement | 2 | 1.5 | -0.5 | James | Done
Add UI Sound Effects and background music | 2 | 4 | 2 | James | In Progress
Move Start, Running, Won, and Lost code into correct methods | 2 | 0.5 | -1.5 | James | Done
Create InventoryItemDetails Prefab for InventoryScene | 2 | 3 | 1 | James | Done | Contains Image and description
Alter Inventory Scene to display equipped Magic | 2 | 3 | 1 | James | Done
Fix Shield Issue | 2 | 0.5 | -1.5 | James | Done | Shield is used even when not selected
Fix Icon appearing below IconSlot | 0.5 | 0.5 | 0 | James | Done
Implement Spider Boss Special Attack | 2 | 2 | 0 | James | Done
Fixed Stopping Icon issue | 2 | 0.5 | -1.5 | James | Done | Icons Stopped when thrown
Hours Assigned | 20.5 | 22
Total Hours | 27
In Progress
Done

## Tasks 03-04 to 03-11
Task | Time Estimated to Complete | Time Spent | Over/Under | Assigned To | Status | Notes
Upgrade to Unity 5 | 1 | 1 |  | James | Done
Have Background load in depending on level | 1.5 | 1 |  | James | Done
Incorporate InventoryItemDatabase | 6 | 9.5 | 3.5 | James | Done
Create Projectile class | 1.5 |  |  | James | TODO
Improve Collision(change to OnEnterStay) | 0.5 |  |  | James | TODO
Add Particle effects to FireBlast and FrostBlast | 2 | 2.5 |  | James | Done
Have Shield work with enemy projectiles | 1.5 |  |  | James | TODO
Adjusted size of textures for Unity 5 | 0.5 | 0.5 |  | James | Done | Result of Unity 5
Reduced code duplication in MagicIcon class | 0.5 | 0.5 |  | James | Done | Update is no longer overriden
Improved LevelStateManager | 0.5 | 0.5 |  | James | Done | Can now get current state, enemy stops moving when level is over
Fix issue that causes enemies to be unkillable | 0.5 | 1 |  | James | Done | Had to remove the methods from the events
Have FlyingEnemy fly | 0.5 | 0.5 |  | James | Done
Hours Assigned | 14 | 17
Total Hours | 16.5
In Progress
Done

## Tasks 02-25 to 03-04
Task | Time Estimated to Complete | Time Spent | Over/Under | Assigned To | Status | Notes
Create Lightning Magic | 3 | 1 | -2 | James | Done
Alter ComparedItem Class to display equipped Magic | 2 |  |  | James | TODO | Still need to alter to show compared magic when looking at magic section
Add Health Bar to enemy class | 2 | 2 | 0 | James | Done
Create Prefab for Orc and Skeleton | 1 | 1 | 0 | James | Done | Similar to Bandit
Create Prefab for Cougar | 0.5 | 0.5 | 0 | James | Done | Similar to Wolf
Spawn Enemy Prefab into level depending on the level selected | 4 | 1.5 | -2.5 | James | Done
Create RangedEnemy class and Archer Prefab | 2 | 2 | 0 | James | Done
Shield works with collisions | 1.5 | 1 | -0.5 | James | Done
Shield uses prefab | 1.5 | 1 | -0.5 | James | Done
Shield Defence text above ShieldControl | 0.5 | 0.5 | 0 | James | Done
Add Stand state to enemy and improve attack movement | 2 | 2 | 0 | James | Done
Total Hours Assigned | 20 | 12.5
TODO
In Progress
Done

## Tasks 02-18 to 02-25
Task | Time Estimated to Complete | Time Spent | Over/Under | Assigned To | Status | Notes
Create FireBlastMagic Class | 1.5 | 2 | 0.5 | James | Done
Create FrostBlastMagic Class | 1.5 | 2 | 0.5 | James | Done | Ran into issue with slowing enemy
Create StandingEnemy Class | 2 | 1 | -1 | James | Done | Will be like a wolf
Create FlyingEnemy Class | 4 | 2 |  | James | Done | Like a Eagle
Create Base Boss Class | 3 | 1.5 | -1.5 | James | Done | Will have a special attack
Create SpiderBoss Class | 2 | 2 |  | James | Done
Alter ComparedItem Class to display equipped Magic | 2 |  |  | James | TODO | Still need to alter to show compared magic when looking at magic section
fix any issues with the Finite state machine for the enemy | 1 | 1 |  | James | In Progress | Fix any troubles discovered during meeting
Move Level State code into a separate class and fix and implementation issues | 2 | 0.5 |  | James | In Progress | Issue with changing state
Fix issue of IconSpawner always spawning FrostBlast Icons | 0.5 | 0.5 | 0 | James | Done
Total Hours Assigned | 19.5 | 12.5
TODO
In Progress
Done

## Tasks 02-11 to 02-18
Task | Time Estimated to Complete | Time Spent | Over/Under | Assigned To | Status | Notes
Expand MagicIcon class | 3 |  |  | James | TODO
Have IconSpawner Spawn in new icons when old ones are used | 1.5 | 0.5 | -1 | James | Done
Fix Base Enemy Collisions with weapon | 1 | 0.5 | -0.5 | James | Done | And make variables public
Create StandingEnemy Class | 2 |  |  | James | TODO | Will be like a wolf
Create FlyingEnemy Class | 4 |  |  | James | TODO
Create Base Boss Class | 3 |  |  | James | TODO
Create ComparedItem Game Object | 2 |  |  | James | TODO | Still need to alter to show compared magic when looking at magic section
Fix Icons and enemies colliding with each other | 3 | 1 | -2 | James | Done
Research and implement Finite state machine for enemy | 4 | 4 |  | James | In Progress
Reduce coupling/Clean up code | 2 | 2.25 | 0.25 | James | Done
Change name of enemy methods to OnXXX | 0.25 | 0.25 | 0 | James | Done
Update MeleeWeapon to take in a prefab and itemImage | 0.5 | 0.5 | 0 | James | Done
Destroy Icons after leaving the camera | 0.25 | 0.25 | 0 | James | Done
Incorporate the FiniteStateMachine into the level to store levelstate | 4 | 3 |  | James | In Progress | Issue with changing state
Total Hours Assigned | 30.5 | 12.25
TODO
In Progress
Done

## Tasks 02-04 to 02-11
Task | Time Estimated to Complete | Time Spent | Over/Under | Assigned To | Status | Notes
Add a RigidBody to the base icon | 0.5 | 0.5 | 0 | James | Done
Create MagicIcon | 1 | 1 | 0 | James | Done
Create CoinIcon | 1 | 0.5 | -0.5 | James | Done | Adds a coin when colliding with coinbag
Create RangedIcon | 1 | 1.5 | 0.5 | James | Done
Have IconSpawner Spawn in new icons when old ones are used | 2.5 | 0.5 |  | James | In Progress
Create Base Enemy Class | 5 | 6 | 1 | James | In Progress | Issue occurring with collisions
Create EnemyPrefab | 0.5 | 0.5 | 0 | James | Done |  | TODO
Create EnemySpawner | 1 | 1 | 0 | James | Done | Will Spawn in Enemy Prefab | In Progress
Create ComparedItem Game Object | 2 |  |  | James | TODO | Still need to alter to show compared magic when looking at magic section | Done
Add iconselect boolean to prevent multiple icons being selected | 0.25 | 0.25 | 0 | James | Done
Script Cleanup | 1 | 1.5 | 0 |  | Done
Total Hours Assigned | 14 | 12.75

## Tasks 01-28 to 02-04
Task | Time Estimated to Complete | Time Spent | Over/Under | Assigned To | Status | Notes
Fill inventory Class with Fake data | 1 | 0.5 | -0.5 | James | Done
Create ActionArea | 1 | 0.5 | -0.5 | James | Done | Appears when the WeaponControl is in use
Create WeaponControl and attach to WeaponControl Game Object | 2 | 2 | 0 | James | Done
Create ShieldControl and attach to ShieldControl Game Object | 2 | 1 | -1 | James | Done | Will not do to much until the enemy is created
Filter InventoryItems based on itemType for Inventory Scene | 2 | 2 | 0 | James | Done
Select inventoryItem with touch in Inventory Scene | 1.5 | 1 | -0.5 | James | Done
Create ComparedItem Game Object | 2 | 2 | 0 | James | In Progress | Still need to alter to show compared magic when looking at magic section
Create SelectedItem Game Object | 2 | 1.25 | -0.75 | James | Done | Game Object will display the select item's information | TODO
Reduce rows in Inventory scene and make slots bigger | 0.5 | 0.25 | -0.25 | James | Done |  | In Progress
Rearrange Inventory Scene UI | 0.5 | 0.25 | -0.25 | James | Done | To show number of health potions and mana potions the player has | Done
Create Sky,Ground, and Background Game Objects | 0.5 | 0.25 | -0.25 | James | Done
Convert unequippedItems to a List | 1 | 0.25 | -0.75 | James | Done
Create Icon Base Class | 2 | 2 | 0 | James | Done | Icon Spawner can spawn these in
Total Hours Assigned | 18 | 13.25